## Sheet1
Activity | member responsible | review on | complete by | depends on task
Revised New Use Case Description "Change Player Settings" | Abdelrahman Ahmed | 7th Mar | 17th March | Iteration 2
Revised New Use Case Description "Change Display Settings" | Saad Equbal | 7th Mar | 17th March | Iteration 2
Revised Sequence Diagrams "Change Player Settings" | Ekuyik Nyong Essien | 7th Mar | 17th March | Iteration 2
Revised Sequence Diagrams "Change Display Settings" | Ujjwal Singla | 7th Mar | 17th March | Iteration 2
Use Case "Main Menu" | Abdelrahman Ahmed | 7th Mar | 17th March
Use Case "Ending a Game" | Saad Equbal | 7th Mar | 17th March
Sequence Diagram "Main Menu" | Ekuyik Nyong Essien | 7th Mar | 17th March | 8
Sequence Diagram "Enging a Game" | Prosper Manyele | 7th Mar | 17th March | 9
Logical Architecture Diagram | Ujjwal Singla | 7th Mar | 17th March